## Sample Plan
ID | Task | Owner | T-Minus Start | T-Minus End | Est. Start | Est. End | Act. Start | Act End | Status | Comments
1.0 | Organization | Conferece Chair | -6 months | -5 months
1.1 | Form Conference Organizing Committee |  | -6 months | -6 months | [5 empty] | A section will need a committee to plan the conference. Ideally it would have a chair, a logistics person, and a PR person. The assumption is that the section will help fund the conference, so the treasurer should also be part of the committee. The chair coordinates the activities. The logistics person helps with venue, catering, and working with chapters to find speakers, and the PR person works with the section marketing and communications lead to promote the event.
1.2 | Set Meeting Cadence |  | -6 months | -6 months | [5 empty] | The organizing committee should meet every other week until 3 months prior to the conference. At that point, the committee should meet weekly. This helps drive urgency and accountability within the committee.
1.3 | Determine Conference Theme |  | -6 months | -5 months | [5 empty] | This is optional. The Theme could be a topic that each speaker would align towards.
2.0 | Overall Logistics | Logistics Lead | -6 months | -2 months
2.1 | Select Conference Theme |  | -5 months | -5 months | [5 empty] | This is optional. The Theme could be a topic that each speaker would align towards.
2.2 | Select Dates |  | -6 months | -6 months | [5 empty] | Sections will need to pick a date that works for the section and the chapters. This typically is a weekend and is for 6 to 8 hours, depending on the number of speakers
2.3 | Determine Conference Location |  | -6 months | -5 months | [5 empty] | Suggestion for this could be a local university or college where rooms can be reserved at no cost. Sections should reach out to their student branches to determine if the branches can reserve rooms at the university.
2.4 | Reserve Space |  | -5 months | -5 months | [5 empty] | Once you determine how many speakers you want to have and how many tracks, work to reserve space at the venue.
2.5 | Find Keynote Speaker |  | -5 months | -4 months | [5 empty] | In the past, sections have had an opening keynote/plenary speaker. If you have a Conference Theme, the speaker should tie to it.
2.6 | Contact Society Chapter Officers and Affinity Groups |  | -6 months | -6 months | [5 empty] | The local Society Chapters and Affinity Groups should be engaged from the start of the planning process (and should participate on your organizing committee). The Society Chapters would be a source of speakers for the conference
2.6 | Obtain Commitment from Society Chapter/Affinity Group Officers for Speakers |  | -5 months | -5 months | [5 empty] | Each Society Chapter and Affinity Group should be provided a slot for a speaker. This will also determine the initial room planning needs
2.7 | Obtain Speaker Topics and Speaker Bios |  | -4 months | -2 months | [5 empty] | At least 2 months prior to the conference, obtain the bios and topics for each speaker so that marketing can communicate that to the section and other adjacent organizations.
2.8 | Decide on admission fee |  | -6 months | -5 months | [5 empty] | Sections should consider charging a nominal fee as part of registration to ensure registrant commitments. Sections can also charge a fee that cover the suggested meals (continenal breakfast and box lunch) as well. Note that some colleges or universities prohibit the charging registration fees as part of their room reservation process.
3.0 | Marketing | PR Lead | -6 months | -2 weeks
3.1 | Determine Conference Costs | Treasurer | -6 months | -4 months | [5 empty] | The treasurer should determine a preliminary budget for the conference. This includes income (registration fees) and expenses (food, rooms, marketing, etc.) The assumption is that this is not a peer reviewed technical conference. If it is, then paper processing (which will need to be covered in a different plan) will need to be considered.
3.2 | Create Conference Flyer/Brochure |  | -5 months | -4 months | [5 empty] | The PR person should create a one page flyer that can be made into a PDF and distributed to Society Chapters, Student Branches, and Affinity Group to distribute among the members. In addition, this would be updated as more information is available.
3.3 | Create vTools Event |  | -3 months | -3 months | [5 empty] | vTools can be used to process registrations as well as collect registration fees from attendees. Include the Society Chapters, Affinity Groups, Student Branches, and any neighboring sections in the vTools host field.
3.4 | Send initial eNotice to section and neighboring sections |  | -3 months | -3 months | [5 empty] | This can be kicked off from the vTools Event page. If you want to offer the conference to neighboring sections, work with the Section Chair(s) from neighboring sections to sponsor the conference and distribute information
3.5 | Submit Event to Newsletter |  | -3 months | -3 months | [5 empty] | If you have a Section newsletter, ensure that the conference is well advertised in it. Work with your neighboring sections to get your event in their newsletter too.
3.6 | Create Conference Website |  | -3 months | -3 months | [5 empty] | Utilize the Section Website to create a page for your conference. Include registration links and a contact person to obtain more information
3.7 | Obtain Exhibitors and/or Patrons |  | -5 months | -2 months | [5 empty] | This is optional. If you want to have exhibitors, identify local businesses who may want to market to our members and offer them space for a fee at the conference. This will mean that you will need a 6'x18" table for each exhibitor/patron.
3.8 | Confirm Exhibitors and/or Patrons |  | -3 months | -1 month | [5 empty] | This is optional. If you have exhibitors or patrons, make sure that you get a commitment and provide them payment instructions.
3.9 | Obtain Exhibitors and/or Patrons Payments |  | -1 month | -2 weeks | [5 empty] | This is optional. For exhibitors and patrons, you will need to collect payment (if required) to exhibit at the conference.
3.10 | Send eNotice to section and neighboring sections |  | -1 month | -1 month | [5 empty] | Resend the eNotice to your Section members and neighboring sections' members to help boost registration
3.11 | Send final registration eNotice to section and neighboring sections |  | -2 weeks | -2 weeks | [5 empty] | Resend the eNotice to your Section members and neighboring sections' members to help boost registration
4.0 | Conference Logistics | Logistics Lead | -4 months | -1 week
4.1 | Confirm Rooms |  | -4 months | -4 months | [5 empty] | Confirm that the rooms are still reserved.
4.2 | Confirm A/V in Rooms |  | -3 months | -3 months | [5 empty] | Confirm that the rooms will have A/V (minimum of a projector and an HDMI cable with an optional microphone and speaker if the space requires it.
4.3 | Obtain Speaker Biographies |  | -2 months | -2 months | [5 empty] | Confirm that speaker bios are received for the Website and for speaker introducers.
4.4 | Assign Room Prep and Speaker Introducers |  | -1 month | -2 weeks | [5 empty] | At this point, assign speakers to speaking slots. The Sample Schedules tab provides an example of this.
4.5 | Determine Food Logistics (Breakfast, Lunch, Mid-Afternoon Snacks) |  | -1 month | -2 weeks | [5 empty] | Consider allergies, food sensitivities, and dietary restrictions.
4.6 | Order Food |  | -2 weeks | -1 week | [5 empty] | Timing of this is dependent on registration cut-off
4.7 | Request Exhibitor and Patron Tables |  | -1 month | -2 weeks | [5 empty] | Timing of this is dependent on patron/exhibitor cut-off
4.8 | Confirm logistsics |  | -1 week | -1 week | [5 empty] | Final review of event logistics one week prior to the event.
5.0 | Day of Conference |  | -2 months | Day of
5.1 | Gather volunteers (speaker guides, guest guides, registration) |  | -2 months | -1 month | [5 empty] | The level of volunteer needs are dependent on the size of the conference. The speaker guides and guest guides are for multi-track conferences where multiple rooms are used.
5.2 | Confirm Speakers and Bios with Society Chapter and Affinity Groups |  | -1 month | -1 month | [5 empty] | Ensure that the Society Chapters and Affinity Groups have their speakers confirmed.
5.3 | Obtain list of attendees |  | -2 weeks | -1 week | [5 empty] | This can be pulled directly from vTools.
5.4 | Assign volunteer duties |  | -1 month | -2 weeks | [5 empty] | Speaker Guides: Guide speakers to their rooms and introduce them at the beginning of the session Guest Guides: Guide attendees to rooms prior to session start Registration: Check people and exhibitors (if any) in and direct them to their table/appropirate area
5.5 | Train volunteers if needed |  | -2 weeks | -1 week
5.6 | Close vTools registration |  | -1 week | -1 week | [5 empty] | Suggest closing registration 1 week prior to the event so that a finalized list of attendees can be locked down
5.7 | Send attendee welcome e-mail/eNotice |  | -5 days | -5 days | [5 empty] | Communicate to the attendees the location and any parking information needed
5.8 | Assign exhibitor and patron space |  | -2 weeks | -1 week | [5 empty] | Optional. Determine where each exhibitor or patron will set up their table
5.9 | Confirm food orders and delivery |  | -3 days | -3 days | [5 empty] | Ensure that food is ordered and prepared for pickup or delivery on conference day
5.10 | Confirm A/V availability |  | -3 days | -3 days | [5 empty] | Work with venue to ensure that A/V is still available in the reserved rooms.
5.11 | Print out sign-in sheets |  | -1 day | -1 day | [5 empty] | This can be pulled directly from vTools
5.12 | Test A/V equipment |  | -2 days | -1 day | [5 empty] | Suggest running a test of all AV equipment prior to the start of the conference
5.13 | Setup registration desk |  | Day of | Day of
5.14 | Run Conference |  | Day of | Day of
6.0 | Post Conference | Conference Chair
6.1 | Conduct lessons learned session |  | Day of | +1 week | [5 empty] | Conduct a debrief no more than 1 week post event
6.2 | Submit vTools report |  | Day of | +1 week | [5 empty] | Ensure that the vTools report is submitted. Include the Society Chapters and Affinity Groups or neighboring sections if they provided support or speakers.
6.2 | Compile lessons learned and share with region/other sections |  | +1 week | +1 month
6.3 | Transfer admission fees from vTools to IEEE Concentration Banking |  | Day of | + 1 month | [5 empty] | This should be done automatically
6.4 | Celebrate end of conference |  | +1 week | +1 month

## Sample Schedules
Time | Common Area | Main Hall | Breakout 1 | Breakout 2 | Breakout 3 | Breakout 4 | Time | Common Area | Main Room
0800 | Registration Breakfast | [5 empty] | 0800 | Registration Breakfast
0815 | [6 empty] | 0815
0830 | [6 empty] | 0830
0845 | [6 empty] | 0845
0900 |  | Opening |  |  |  |  | 0900 |  | Opening
0915 |  | Keynote |  |  |  |  | 0915 |  | Speaker
0930 | [6 empty] | 0930
0945 | [6 empty] | 0945 |  | Speaker
1000 | [6 empty] | 1000
1015 |  | Break | Speaker Prep | Speaker Prep | Speaker Prep | Speaker Prep | 1015 |  | Break
1030 |  |  | Speaker | Speaker | Speaker | Speaker | 1030 |  | Speaker
1045 | [6 empty] | 1045
1100 |  | Lunch Prep |  |  |  |  | 1100 |  | Speaker
1115 | [6 empty] | 1115 | Lunch Prep
1130 |  | Lunch |  |  |  |  | 1130 |  | Lunch
1145 | [6 empty] | 1145
1200 | [6 empty] | 1200
1215 |  |  | Speaker Prep | Speaker Prep | Speaker Prep | Speaker Prep | 1215
1230 |  |  | Speaker | Speaker | Speaker | Speaker | 1230 |  | Speaker
1245 | [6 empty] | 1245
1300 | [6 empty] | 1300 |  | Speaker
1315 |  | Break |  |  |  |  | 1315
1330 |  |  | Speaker Prep | Speaker Prep | Speaker Prep | Speaker Prep | 1330 |  | Break
1345 |  |  | Speaker | Speaker | Speaker | Speaker | 1345 |  | Speaker
1400 | [6 empty] | 1400
1415 | [6 empty] | 1415 |  | Speaker
1430 |  | Break |  |  |  |  | 1430
1445 |  |  | Speaker Prep | Speaker Prep | Speaker Prep | Speaker Prep | 1445 |  | Closing Remarks
1500 |  |  | Speaker | Speaker | Speaker | Speaker | 1500
1515 | [6 empty] | 1515
1530 | [6 empty] | 1530
1545 |  | Break |  |  |  |  | 1545
1600 |  | Closing Remarks |  |  |  |  | 1600
1615 | [6 empty] | 1615
1630 | [6 empty] | 1630
1645 | [6 empty] | 1645
| Option 1 - Multi-track conference with 45-minute speakers | [6 empty] | Option 2 - Single track conference with 30 minute speakers